## Bill 1
BILL OF ENGINEERING MEASUREMENT AND EVALUATION FOR THE REHABILITATION OF EXISTING FOUR (4NO.) MINI-SEWAGE TREATMENT PLANTS (AERATORS) IN GUDU, KATAMPE EXTENSION DISTRICTS AND SANI ABACHA BARRACKS IN THE CITY.
ITEM | DESCRIPTION | UNIT | Amount | [5 empty] | AMOUNT N : K
Balance from BEME
|  |  | BEME | Utilized | Remaining | Extra Over | Additional requirement | Additional requirement + 12.5% | Total Submission
|  | A | B | C | D=B-C |  | F | G=F*1.125 | H=D+G
BILL NO. 1 - GENERAL
1.01 | Allow for monthly progress photographs | PS | 100000 | 0 | 100000 | 0 |  | 0 | 100000
1.02 | Provide and maintain functional office accomodation for Engineer's representative and staff as directed | PS | 2500000 | 377730 | 2122270 | 0 | 4000000 | 4500000 | 6622270
1.03 | Provide furniture for the office of the Engineer's representative and staff | PS | 2000000 | 0 | 2000000 | 0 | 5000000 | 5625000 | 7625000
1.04 | Allow for the settlement of monthly bills(PHCN, Water, Communication and AEPB) | PS | 1200000 | 281250 | 918750 | 0 | 24000000 | 27000000 | 27918750
1.05 | Allow for payment of wages and allowances to daily rated staff of the Engineer's Rep. | PS | 2400000 | 13845937.5 | 0 | 11445937.5 | 11025000 | 12403125 | 23849062.5 | 30 | 0
1.06 | Allow for the supply and installation of computers, printers, copiers, graphic plotters and other accessories | PS | 1500000 | 900000 | 600000 | 0 | 4000000 | 4500000 | 5100000
1.07 | Allow for the cost of stationeries required for Engineer's Rep. | PS | 600000 | 0 | 600000 | 0 |  | 0 | 600000
1.08 | Allow for purchase of Toyota Avensis saloon car or similar approved. | PS | 11000000 | 0 | 11000000 | 0 | 25000000 | 28125000 | 39125000
1.09 | Allow for purchase of Four Wheel drive double cabin pick up or similar approved | PS | 7500000 | 0 | 7500000 | 0 | 30000000 | 33750000 | 41250000
1.1 | Allow for comprehensive insurance, registration, security installation, logo painting and other sundry services for vehicles | PS | 800000 | 0 | 800000 | 0 | 2500000 | 2812500 | 3612500
1.11 | Allow for maintenance of the project vehicles | PS | 1400000 | 0 | 1400000 | 0 | 4000000 | 4500000 | 5900000
1.12 | Allow for fueling of vehicles | PS | 2500000 | 4451400 | 0 | 1951400 | 3726500 | 4192312.5 | 6143712.5
1.13 | Allow for relocation of existing infrastructure services as may be directed by Engineer's rep. | PS | 2500000 | 1653750 | 846250 | 0 | 2500000 | 2812500 | 3658750
1.14 | Allow for production of as built drawings (5 copies) as may be directed by the Engineer | PS | 800000 | 0 | 800000 | 0 | 2500000 | 2812500 | 3612500
1.15 | Testing and commissioning of the electrical and mechanical equipment of the aerators. | PS | 800000 | 0 | 800000 | 0 | 2000000 | 2250000 | 3050000
1.16 | Provide and erect publicity signs as directed by the Engineer in accordance with MOR & PW standard drawings. | PS | 180000 | 0 | 180000 | 0 | 1500000 | 1687500 | 1867500
1.17 | Allow for services to Engineer's Representative (Survey Instrument, etc) | PS | 1000000 | 0 | 1000000 | 0 | 5000000 | 5625000 | 6625000
1.18 | Environmental Impact Assessment detail reports | PS | 8000000 | 956250 | 7043750 | 0 | 8000000 | 9000000 | 16043750
| Total Carried to Summary Page |  | 46780000 | 22466317.5 |  |  |  |  | 202703795

## Other
BILL OF ENGINEERING MEASUREMENT AND EVALUATION FOR THE REHABILITATION OF EXISTING FOUR (4NO.) MINI-SEWAGE TREATMENT PLANTS (AERATORS) IN GUDU, KATAMPE EXTENSION DISTRICTS AND SANI ABACHA BARRACKS IN THE CITY.
ITEM | DESCRIPTION | UNIT | QUANTITY |  |  |  |  | RATE |  | AMOUNT N : K
|  |  | BEME | Executed | Outstanding | Additional Works | New Quantity | BEME | Proposed | Total Submission
BILL NO.2 - CIVIL WORKS
2.01 | Clear site around the ponds of all bushes, grass, shrubs etc and cart away. | m2 | 2500 | 2500 | 0 | 2500 | 2500 | 200 | 200 | 500000
2.02 | Remove vegetation undergrowth at beds and sides Of ponds, grub up roots, dispose off and apply prescribed herbicide, | m2 | 4900 | 2000 | 2900 | 4900 | 7800 | 200 | 200 | 1560000
2.03 | Where paved surfaces are intact and as directed by the engineer, allow for removal of grass from joints, application of the prescribed herbicide and re-jointing and pointing in sand cement mortar. | m2 | 600 | 0 | 600 |  | 600 | 900 | 900 | 540000
2.04 | Ditto but sulphate resistant sand mortar to joints. | m3 | 120 | 0 | 120 |  | 120 | 1500 | 1500 | 180000
2.05 | Excavate and cart away unsuitable material. | m3 | 1000 | 0 | 1000 |  | 1000 | 1200 | 1200 | 1200000
2.06 | Rehabilitate the bridge steel by grinding and painting them with sea air resistant paint. | m2 | 50 | 0 | 50 |  | 50 | 6000 | 6000 | 300000
2.07 | Rehabilitate the steel gutters by grinding and painting them with sea air resistant paint. Ditto as item 2. | m2 | 30 | 0 | 30 |  | 30 | 7000 | 7000 | 210000
2.08 | Supply and Apply Concrete Manhole Covers that can withstand 200 kg/m2. | No. | 10 | 5 | 5 |  | 5 | 8500 | 8500 | 42500
2.09 | Rehabilitate and treat the cracked concrete with special materials to fill the cracks. | m3 | 30 | 0 | 30 |  | 30 | 1800 | 1800 | 54000
2.1 | Replace the broken glass with new one of 6 mm thickness. | m2 | 60 | 0 | 60 |  | 60 | 35000 | 35000 | 2100000
2.11 | Supply a steel bin for the grits having a volume of 1.5 m3. | No. | 4 | 0 | 4 |  | 4 | 135000 | 135000 | 540000
2.12 | Supply and apply Penstock Valve of Stainless Steel- 316L. 102x102 cm | No. | 5 | 0 | 5 |  | 5 | 9500 | 9500 | 47500
2.13 | Allow for flushing of the screen chamber, carrying out the necessary repairs and unblocking the adjoining sewer as directed by the Engineer (Provisional). | PS |  | 0 | 0 |  |  |  |  | 0
2.14 | Provide and fix mesh wire fence, including barbed wire (3 rows) | m | 623 | 410 | 213 |  | 213 | 25000 | 25000 | 5325000
2.15 | Alow for replacement of guardrails, bridge steel and stairs as directed by the Engineer(ProvisionaI). | PS |  | 0 | 0 |  |  |  |  | 0
2.16 | Provide all materials and repair interpond connection inlets as directed by the Engineer(Provisional). | PS |  | 0 | 0 |  |  |  |  | 0
2.17 | Plant approved grass on all outer slopes at embankment, including watering, manure etc till fully established. | m2 | 1800 | 0 | 1800 |  | 1800 | 650 | 650 | 1170000
2.18 | Painting of Offices | m2 | 500 | 100 | 400 |  | 400 | 950 | 950 | 380000
| Carried Forward | [8 empty] | 14149000
| Brought Forward | [8 empty] | 14149000
NEW ITEMS
N2.0 | Civil Works
N2.01 | Evacuation of slugde from the Tanks in the 4 (Four) Sites. | Nos |  |  |  | 4 | 4 |  | 1750000 | 7000000
N2.02 | Construction of V-chanell Drainage and sand trap at Apo Aerator | m3 |  |  |  |  | PS |  | 1200000 | 1200000
N2.03 | Fence Work at Apo Aerator | m
| Demolition of existing fence and cart away of the debris | PS | [6 empty] | 100000 | 100000
N2.0311 | Excavate trench for foundation not exceeding 800mm depth | m |  |  |  | 222 | 222 |  | 1500 | 333000
N2.032 | Level and compact bottom of excavation to receive concrete foundation | m |  |  |  | 153 | 153 |  | 400 | 61200
N2.033 | Remove excavated material from site | m |  |  |  | 184 | 184 |  | 500 | 92000
N2.034 | Backfilling both sides of the wall | m3 |  |  |  | 54 | 54 |  | 500 | 27000
N2.035 | Mass concrete to foundation well mixed to engineer's specification | m |  |  |  | 3 | 3 |  | 45000 | 135000
N2.04 | Block Work
N2.041 | 225mm hollow block work filled solid | m |  |  |  | 363 | 363 |  | 4500 | 1633500
N2.042 | 225mm hollow block work cement and sand | m |  |  |  | 523 | 523 |  | 4000 | 2092000
N2.05 | Concrete Work
N2.051 | Concrete coping | m3 |  |  |  | 3 | 3 |  | 45000 | 135000
N2.052 | Ditto to block pillars | m3 |  |  |  | 4 | 4 |  | 4500 | 18000
N2.06 | Form Work
N2.061 | Form work to side of coping | m |  |  |  | 67 | 67 |  | 1500 | 100500
N2.062 | Ditto to block pillars | m |  |  |  | 15 | 15 |  | 1500 | 22500
N2.07 | Renovation of 4 site offices at Gudu, Apo, Katampe and Abacha Barracks Site | No. |  |  |  | 4 | 4 |  | 5000000 | 20000000
N2.08 | Construction of Concrete Passage at Abacha Barracks Aerator |  |  |  |  | 16 | 16 |  | 45000 | 720000
N2.09 | Provision of Bore hole and Tank for Abacha Barracks Aerator | PS |  |  |  | 1 | 1 |  | 12000000 | 12000000
N2.10 | Reconnection of water supply to water board for Kamtempe, Gudu and Apo site | PS |  |  |  | 3 | 3 |  | 1000000 | 3000000
| Total Carried to Summary Page | [8 empty] | 62818700
BILL NO.3 - ELECTRICAL WORKS
GENERATOR WORKS
3.01 | Provision of 250KVA Automatic Sound Proof Generating Set | No | 3 | 0 | 3 |  | 3 | 16675000 | 16675000 | 50025000
3.02 | Allow for installation of Generator ie Plinth, 10,000 Litres diesel tank, support structure and plumbing works | No | 3 | 0 | 3 |  | 3 | 2610000 | 2610000 | 7830000
3.03 | Provision For synchronizing & automatic mains failure Panel | No | 3 | 0 | 3 |  | 3 | 1087500 | 2305000 | 6915000
3.04 | Provision for 400A gear switch | No | 3 | 0 | 3 |  | 3 | 507500 | 1015000 | 3045000
3.05 | Provision for 400A changeover switch | No | 3 | 0 | 3 |  | 3 | 609000 | 1218000 | 3654000
11KV OVERHEAD LINE WORKS
3.06 | Provision of existing 11KV Section Pole Assembly | No | 3 | 2 | 1 |  | 1 | 246500 | 493000 | 493000
3.07 | Provision of 11KV Lightning Arrester | No | 4 | 2 | 2 |  | 2 | 72500 | 174000 | 348000
3.08 | Provision of 11KV D-Fuse | No | 4 | 0 | 4 |  | 4 | 69600 | 189200 | 756800
3.09 | Provision of 1 x 70mm2 XLPE 11KV Cable | M | 260 | 210 | 50 |  | 50 | 8265 | 16530 | 826500
3.1 | Earthing of 11KV Section Pole Assembly | No | 2 | 2 | 0 |  |  | 43500 | 87000
3.11 | Provision of 11KV 3-Member Pole Assembly | No | 1 | 1 | 0 |  |  | 369750 | 737500
3.12 | Provision of 10.5m concrete pole (C & C) | No | 10 | 7 | 3 |  | 3 | 79750 | 159599 | 478797
3.13 | Dressing of 11kv Intermediate pole | No | 5 | 0 | 5 |  | 5 | 25000 | 50000 | 250000
3.14 | Provision of 150mm2 Aluminium Conductor | M | 1000 | 417 | 583 |  | 583 | 1300 | 2600 | 1515800
3.15 | Provision for 11KV Reychem Termination 1 x 70mm2 | Set | 8 | 4 | 4 |  | 4 | 65250 | 130500 | 522000
| 33KV OVERHEAD LINE WORKS |  |  |  | 0
3.16 | Provision of 33KV Section Pole Assembly | No | 2 | 0 | 2 |  | 2 | 185000 | 370000 | 740000
3.17 | Provision of 33KV Lightning Arrester | No | 1 | 0 | 1 |  | 1 | 87000 | 174000 | 174000
3.18 | Provision of 33KV D-Fuse | No | 1 | 0 | 1 |  | 1 | 65000 | 130000 | 130000
3.19 | Provision of 1 x 70mm2 XLPE 33KV Cable | M | 100 | 0 | 100 |  | 100 | 8265 | 16530 | 1653000
3.2 | Earthing of 33KV Section Pole Assembly | No | 2 | 0 | 2 |  | 2 | 43500 | 87000 | 174000
3.21 | Provision of 33KV 3-Member Pole Assembly and earthing | No |  | 0 | 0 | 1 | 1 | 265000 | 265000 | 265000
3.22 | Provision of 10.5m concrete pole (C & C) | No | 4 | 0 | 4 |  | 4 | 79750 | 159500 | 638000
3.23 | Dressing of 33kv Intermediate pole | No | 0 | 0 | 0 |  |  | 40000
3.24 | Provision of 150mm2 Aluminium Conductor | M | 60 | 0 | 60 |  | 60 | 1300 | 2600 | 156000
3.25 | Provision for 33KV Reychem Termination 1 x 70mm2 | Set | 4 | 0 | 4 |  | 4 | 65250 | 130500 | 522000
| Carried Forward | [8 empty] | 81111897
| Brought Forward | [8 empty] | 81111897
SUBSTATION WORKS
3.26 | Outdoor conventional substation 500 KVA,11KV/400V, incl. outer earthing system. | nos | 1 | 1 | 0 |  | 1 | 4060000 | 8120000 | 8120000
0.01 | Provide mix and place C30 reinforced concrete in foundation for 33/04 KV-sub-station incl. excavation, blinding, shuttering, reinforcement and backfilling as specified and fencing | nos | 1 | 1 | 0 |  | 1 | 1800000 | 1800000 | 1800000
3.27 | Factory assembled outdoor package substation 500 KVA,11KV/400V, incl. outer earthing system. | nos | 2 | 0 | 2 |  | 2 | 14000000 | 28000000 | 56000000
0.02 | Provide mix and place C30 reinforced concrete in foundation for 11/04 KV-sub-station incl. excavation, blinding, shuttering, reinforcement and backfilling as specified, fencing..etc | nos | 2 | 0 | 2 |  | 2 | 1400000 | 1400000 | 2800000
3.28 | 11KV – Cable, Type XLPE 1 x 300mm2 to be drawn into closed conduit system laid into trenches | m |  |  | 0 |  |  |  |  | 0
[5 empty] | 0 |  |  |  |  | 0
| L.V CABLES AND ACCESSORIES TO SPECIFICATION AND RELEVANT DRAWINGS | [8 empty] | 0
3.29 | 0.6/1KV-Cable, identical to Type NYFGY or equivalent 4 x 120mm2 to be laid in trenches and to be drawn into conduits (road crossings) | m |  | 0 | 0 |  |  | 48000 |  | 0
3.3 | ditto , but cable with 4 x 95mm2 | m | 900 | 355 | 545 |  | 545 | 41700 | 41700 | 22726500
3.31 | ditto , but cable with 4 x 50mm2 | m | 350 | 0 | 350 |  | 350 | 18450 | 36900 | 12915000
0
| SERVICE FEEDER PILLARS | [8 empty] | 0
3.32 | 400A Feeder pillar with 6 ways TPN complete with fuse bases and fuses 30A - 100A | nos | 3 | 1 | 2 |  | 2 | 480000 | 960000 | 1920000
3.33 | Set of earthing material for feeder pillar | nos | 3 | 1 | 2 |  | 2 | 18000 | 36000 | 72000
3.34 | Set of equipment for control room, inl. Mimic panel and control cables as specified. | nos | 3 | 0 | 3 |  | 3 | 150000 | 300000 | 900000
3.35 | Set of material for repair purposes | P.S |  | 0 | 0
3.36 | Cable trench Type 3, including excavation, backfilling, sand surround, concrete protection slabs, warning tape, width = 60cm, depth up to 1.10m | m | 1300 | 300 | 1000 |  | 1000 | 6000 | 12000 | 12000000
3.37 | ditto as item 11.49.1 but trench Type 4, width = 120cm, depth up to 1.10m | m | 800 | 120 | 680 |  | 680 | 6000 | 12000 | 8160000
3.38 | Provide mix and place C30 reinforced concrete in foundation for distribution boards incl. excavation, blinding, shuttering, reinforcement and backfilling as specified. | nos | 6 | 0 | 6 |  | 6 | 58000 | 116600 | 699600
3.39 | Provide reinforced concrete cable markers section 20 x 15cm, hieght = 1.40m | nos | 28 | 0 | 28 |  | 28 | 30000 | 60000 | 1680000
3.4 | Allow for Testing and commisioning by PHCN and Federal Min. of Power. | P.S |  | 0 | 0 |  |  |  |  | 6000000
| Carried Forward | [8 empty] | 216904997
| Brought Forward | [8 empty] | 216904997
Others
3.41 | 30 amps industrial socket to male and female 3-phase | No | 8 |  | 8 |  | 8 | 32500 | 65000 | 520000
3.42 | The replacement of automatic circuit breaker in the panel | No | 15 |  | 15 |  | 15 | 55000 | 110000 | 1650000
3.43 | Servicing of the panels, (a) relays, (b) contactors, (c) all the circuit breakers | PS |  |  | 0 |  |  |  |  | 0
3.44 | Replacement of external light bulbs, 250watts halogen | No | 120 |  | 120 |  | 120 | 6000 | 18000 | 2160000
3.45 | Changing of control cables due to damage by rats and rodents | PS |  |  | 0 |  |  |  |  | 0
3.46 | Replacement of 3-phase volt meter | No | 8 |  | 8 |  | 8 | 70000 | 140000 | 1120000
3.47 | Internal electrical maintenance for the offices | PS |  |  |  | PS | PS | 600000 | 600000 | 600000
3.48 | Replacing Change Over Switch | PS |  |  |  | PS | PS | 120000 | 120000 | 120000
NEW ITEMS
N3.01 | Electrical Works
N3.02 | Provision of 500KVA,33/0.415KV Transformer | No |  |  |  | 2 | 2 |  | 28000000 | 56000000
N3.03 | Provision of 500mm2 cable single core | m |  |  |  | 60 | 60 |  | 62000 | 3720000
N3.04 | Provision of 500mm2 cable single core LUG | m |  |  |  | 20 | 20 |  | 5000 | 100000
N3.05 | Provision of 4x120mm cable | m |  |  |  | 56 | 56 |  | 500000 | 28000000
N3.06 | Provision of 1x35mm XLPE 33kva | m |  |  |  | 60 | 60 |  | 30000 | 1800000
N3.07 | Provision of 400KVA, 3-Phase, 415V/240V 50 Hz Automatic Sound Proof Generating Set | NO |  |  |  | 3 | 3 |  | 32680000 | 98040000
N3.08 | 0.6/1KV-Cable, identical to Type NYFGY or equivalent 4 x 150mm2 to be laid in trenches and to be drawn into conduits (road crossings) | M |  |  |  | 900 | 900 |  | 110000 | 99000000
N3.09 | Supply and install Circuit breaker 600A at Apo Site control Room (updating the Breaker from 400A to 600A | NO |  |  |  | 1 | 1 |  | 400000 | 400000
N3.09 | provision of Maximium Demand meter for Apo,Abacha Barracks and Gudu site | NO |  |  |  | 3 | 3 |  | 600000 | 1800000
N3.11 | Replacement of rusted Iron platform at Abacha Barracks | PS |  |  |  |  | PS |  | 5000000 | 5000000
N3.12 | Reconstruction of the power line from Gudu Transformer to Nepa power Substation 200m including excavation and covering of the cable. | m |  |  |  | 200 | 200 |  | 110000 | 22000000
N3.13 | 800A Feeder pillar with 6 ways TPN complete with fuse bases and fuses 30A - 100A at Abacha Barracks |  |  |  |  | 2 | 2 |  | 800000 | 1600000
N3.14 | 800A 4Phases Industrial Circuit Breaker at Apo site |  |  |  |  | 1 | 1 |  | 600000 | 600000
N3.15 | 800A 4Phases Industrial Circuit Breaker at Abacha Barracks | No |  |  |  | 1 | 1 |  | 600000 | 600000
N3.14 | Prosivion of 150mm2 Alumminium Conductor in Abacha Barracks | m |  |  |  | 400 | 400 |  |  | 0
N3.16 | Provide handrail 25mm dia hollow section galvanised iron vertical support at 2m interval at Abacha | m |  |  |  | 168 | 168 |  | 8500 | 1428000
N3.17 | Prosision of 24months NEPA Bill for the 4 sites operation | monthly |  |  |  | 24 | 24 |  | 300000 | 7200000
N3.18 | Provision of fire fighting Box for the sites. | Nos |  |  |  | 4 | 4 |  | 500000 | 2000000
N3.19 | Provide 35mm XLPE cable at Abacha Barracks | m |  |  |  | 120 | 120 |  |  | 0
N3.20 | Provision of First Aid Box for the sites | Nos |  |  |  | 4 | 4 |  | 1000000 | 4000000
N3.21 | provision for operation and maintenance of the four sites for 24 months | monthly |  |  |  | 96 | 96 |  | 300000 | 28800000
| Total Carried to Summary Page | [8 empty] | 585162997
BILL NO.4 - MECHANICAL WORKS
4.01 | General service of the pumps and the controls | PS
4.02 | Servicing of uplift pumps | PS
4.03 | Generator servicing | PS |  | PS | 0 |  | 0 | 120000 | 120000 | 120000
4.04 | Provision of diesel for generator | Liter | 60000 | 0 | 60000 |  | 60000 | 330 | 1500 | 90000000
4.05 | Provide and install 4" Gate VALVE | No | 7 | 0 | 7 |  | 7 | 28000 | 90000 | 630000
4.06 | Allow for the replacement of broken down parts of the electromechanical plants | PS |  | 0 |  |  | 0 | 20000000 |  | 20000000
4.07 | provide and fix immersible aerator type 1200TA Motor: housing mild steel casing with paint protection Aerator Parts: stainless steel complete, including accessories and switching station Aspiration Rate: 412Nm/h Power Consumption: 26kw Rate Of Oxygen Transfer: 33.5kg/h stationary between guide tubes in the aeration basin 12 x 12m submergence 3.80m | Nos | 3 | 1 | 2 |  | 2 | 7500000 | 15000000 | 30000000
4.08 | Screen board, galvanized steel plate (0.5 x 0.25 x 0.7m) | Nos | 3 | 0 | 3 |  | 3 | 24000 | 48000 | 144000
4.09 | Inlet to final setting basin, galvanized steel plate (0.5 x 0.25m) | Nos | 5 | 0 | 5 |  | 5 | 24000 | 48000 | 240000
4.1 | Galvanized steel screen, 1.0 x 1.50m thickness 3.5cm including frame | Nos | 4 | 0 | 4 |  | 4 | 24000 | 48000 | 192000
4.11 | Draining board, galvanized steel, 1.25 x 1.00m holes of 20mm | Nos | 5 | 0 | 5 |  | 5 | 18000 | 21600 | 108000
4.12 | Steel beam IPB 160, 1=12.30m | Nos | 3 | 0 | 3 |  | 3 | 7500 | 15000 | 45000
4.13 | Inspection bridge, 0.8m wide, length 4m, including hand railing | Nos | 2 | 0 | 2 |  | 2 | 412500 | 495000 | 990000
4.14 | Overflow steel arris, L=12.0m | Nos | 3 | 0 | 3 |  | 3 | 160000 | 192000 | 576000
4.15 | Provisional extra for “AERAZEN” box blowers with pipe work to pond and control panel | Nos | 4 | 0 | 4 |  | 4 | 100000 | 35000000 | 140000000
4.16 | Grassing of slopes | m2 | 800 | 0 | 800 |  | 800 | 2200 | 2640 | 2112000
4.17 | Provide and fix single leaf door | Nos | 3 | 1 | 2 |  | 2 | 95000 | 114000 | 228000
4.18 | Ditto, but double wing gate | Nos | 3 | 0 | 3 |  | 3 | 280000 | 560000 | 1680000
[7 empty] | 0 |  |  | 0
| NEW ITEMS | [5 empty] | 0 |  |  | 0
N4.0 | Mechanical
N4.01 | Supply and install 15kw return slugdge pump, pump sige DN100 to DN200 with a flow rate of 100l/s and Head of 100m. The motor speed 2900rpm for Abacha Baracks site |  |  |  |  | 2 | 2 |  | 7500000 | 15000000
N4.02 | Supply and install 15kw return slugdge pump, pump sige DN100 to DN200 with a flow rate of 100l/s and Head of 100m. The motor speed 2900rpm for Apo site and Gudu sites |  |  |  |  | 4 | 4 |  | 7500000 | 30000000
N4.03 | Supply and install 37kw Siemens electric motor, three phase 50Hz with motor speed of 14700rpm for Katampe site |  |  |  |  | 5 | 5 |  | 12000000 | 60000000
4.04
| Total Carried to Summary Page | [8 empty] | 392065000
SUMMARY PAGE
| Total for Bill No. 1 - General | [8 empty] | 202703795
| Total for Bill No. 2 - Civil Works | [8 empty] | 62818700
| Total for Bill No. 3- Electrical Works | [8 empty] | 585162997
| Total for Bill No. 4- Mechanical Works | [8 empty] | 392065000
| Sub-Total | [8 empty] | 1242750492
| Add 10% Contigency | [8 empty] | 124275049.2
| Sub-Total | [8 empty] | 1367025541.2
| Add 7.5% V.A.T | [8 empty] | 102526915.59
| Total | [8 empty] | 1469552456.79